## Suppliers
Wave 1 & 2 Suppliers | Alternate Suppliers Identified (List Supplier or No) | Supplier(s) Selected (List Suppliers or No) | Actively Being Worked By India Engineering (Y/N) | Substantiation Requirements Determined and Documented (Y/N) | Expected Exit Date
A H Machine
Alexandria Extrusion
Ametek Thermal Systems
Bryant Rubber
Cherokee Nation Red Wing
Deringer-Ney
Orange County Name Plate
R D Rubber Technology
Robrad Tool & Engineering
Seal Dynamics
TA Aerospace
ROGERSON AIRCRAFT EQUIPMENT GROUP | PHAOSTRON INSTRUMENT & ELECTRONIC COMPANY: 008255879, KANEY AEROSPACE: 005170691 |  | John Kemmer

## Part Scope
Component PN | Wave | Existing Project? | Status | Target 2nd Source Date | EPA / TDR Chief Approval Date | Assignee | EPA Completed (Y/N) | TDR Required (Y/N) | TDR Scheduled or Date Held
100-111498-01 | Wave 0 | A00027 |  |  |  |  | N | Y
100-111501-00 | Wave 0 | A00027 |  |  |  |  | N | Y
100-111502-01 | Wave 0 | A00027 |  |  |  |  | N | Y
100-111608-01 | Wave 0 | Not on Aloha |  |  |  |  | N | Y
3034246-1 | Wave 0 | G00702 |  |  |  | Esaw H. | N | Y
3034247-1 | Wave 0 | G00702 |  |  |  | Esaw H. | N | Y
3036111-2 | Wave 0 | G00702 |  |  |  | Esaw H. | N | Y
3176705-4 | Wave 0 | A00034 |  |  |  |  | N | Y
3844908-111 | Wave 0 | G00703 |  |  |  |  | N | Y
3884538-6 | Wave 0 | G00707 |  |  |  |  | N | Y
70720170-3 | Wave 0 | G00707 |  |  |  |  | N | Y
8524362-1 | Wave 0 | E19016 |  |  |  |  | N | Y
S8168-22A0220 | Wave 0 | [5 empty] | N | Y
3178829-1 | Wave 1 | E19017 | Underway | 2019-08-28 | 2019-06-14 | Terry K | N | Y | 2019-06-07
211-057-9601 | Wave 2 |  | ID'd Not Started | 2019-03-29 | 2019-06-07 | K. Haga | N | Y | 2019-05-31
211-057-9602 | Wave 2 |  | ID'd Not Started | 2019-03-29 | 2019-06-07 | K. Haga | N | Y | 2019-05-31
211-073-9602 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-06-07 | K. Haga | N | Y | 2019-05-31
211-073-9601 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-06-07 | K. Haga | N | Y | 2019-05-31
211-073-9603 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-06-07 | K. Haga | N | Y | 2019-05-31
211-073-9604 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-06-07 | K. Haga | N | Y | 2019-05-31
211-073-9501 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-06-07 | K. Haga | N | Y | 2019-05-31
211-073-9109 | Wave 2 |  | ID'd Not Started | 2019-03-29 | 2019-06-07 | K. Haga | N | Y | 2019-05-31
211-073-9605 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-06-07 | K. Haga | N | Y | 2019-05-31
211-073-9111 | Wave 2 |  | ID'd Not Started | 2019-03-29 | 2019-06-07 | K. Haga | N | Y | 2019-05-31
2-310-046-06 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-05-24 | Ken H. | N | Y | 2019-05-17
2-310-046-12 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-05-24 | Ken H. | N | Y | 2019-05-17
3093578-2 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-05-24 | Ken H. | N | Y | 2019-05-17
3093578-1 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-05-24 | Ken H. | N | Y | 2019-05-17
211-594-9208 | Wave 2 |  | ID'd Not Started | 2019-03-29 | 2019-05-24 | Ken H. | N | Y | 2019-05-17
211-594-9011 | Wave 2 |  | ID'd Not Started | 2019-03-29 | 2019-05-24 | Ken H. | N | Y | 2019-05-17
211-594-9212 | Wave 2 |  | ID'd Not Started | 2019-03-29 | 2019-05-24 | Ken H. | N | Y | 2019-05-17
211-594-9109 | Wave 2 |  | ID'd Not Started | 2019-03-29 | 2019-05-24 | Ken H. | N | Y | 2019-05-17
211-594-9220 | Wave 2 |  | ID'd Not Started | 2019-03-29 | 2019-05-24 | Ken H. | N | Y | 2019-05-17
647-2002-002 | Wave 1 |  | ID'd Not Started | 2019-02-01 | 2019-05-17 | Terry K | N | Y | 2019-05-10
63508564-2 | Wave 1 |  | ID'd Not Started | 2019-05-31 | 2019-04-26 | Terry K | N | Y | 2019-04-19
63508564-1 | Wave 1 |  | ID'd Not Started | 2019-05-31 | 2019-04-26 | Terry K | N | Y | 2019-04-19
63508565-2 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-04-26 | Terry K | N | Y | 2019-04-19
63508565-1 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-04-26 | Terry K | N | Y | 2019-04-19
82010095-002 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-04-05 | Esaw H. | N | Y | 2019-04-05
3181113-1 | Wave 1 |  | Underway | 2019-08-28 | 2019-05-03 | Rick C | N | Y | 2019-04-26
3178489-1 | Wave 1 |  | Underway | 2019-08-28 | 2019-05-03 | Rick C | N | Y | 2019-04-26
2-310-084-01 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-05-24 | Ken H. | N | Y | 2019-05-17
7000037-1019 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
60001376-1 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
7000037-227 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
7000037-253 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
7000037-241 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
7000037-250 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
7000037-179 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
7000037-211 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
7000037-1018 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
7000037-278 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
7000037-150 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
7000037-103 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
7000037-305 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
7000037-1017 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
7000037-304 | Wave 1 |  | Underway | 2019-08-28 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
402-6072-211 | Wave 1 |  | Underway | 2019-08-28 | 2019-05-17 | Agatha B. | N | Y | 2019-05-10
075-05133-0001 | Wave 1 |  | ID'd Not Started | 2019-07-31 | 2019-05-17 | Agatha B. | N | Y | 2019-05-10
67410088-1 | Wave 1 |  | ID'd Not Started | 2019-11-01 | 2019-05-17 | Dina E. | N | Y | 2019-05-10
519957-1 | Wave 1 |  | ID'd Not Started | 2019-04-30 | 2019-05-17 | Dina E. | N | Y | 2019-05-10
59000225-001 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-04-12 | Esaw H. | N | Y | 2019-04-05
59002270-001 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-04-12 | Esaw H. | N | Y | 2019-04-05
2608972-264 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-04-12 | Esaw H. | N | Y | 2019-04-05
59000126-001 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-04-12 | Esaw H. | N | Y | 2019-04-05
2306140-1 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-05-10 | Dina E. | N | Y | 2019-05-03
3038242-1 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-05-31 | Esaw H. | N | Y | 2019-05-24
3038243-1 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-05-31 | Esaw H. | N | Y | 2019-05-24
68004032-101 | Wave 1 |  | ID'd Not Started | 2019-07-31 | 2019-05-03 | Agatha B. | N | Y | 2019-04-26
67041586-1 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-05-10 | Dina E. | N | Y | 2019-05-03
67041586-2 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-05-10 | Dina E. | N | Y | 2019-05-03
67041586-4 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-05-10 | Dina E. | N | Y | 2019-05-03
67041586-3 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-05-10 | Dina E. | N | Y | 2019-05-03
3034246-1 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-05-24 | Esaw H. | N | Y | 2019-05-17
3034247-1 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-05-24 | Esaw H. | N | Y | 2019-05-17
3036111-2 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-05-24 | Esaw H. | N | Y | 2019-05-17
2608972-254 | Wave 1 |  | ID'd Not Started | 2019-10-01 | 2019-04-12 | Esaw H. | N | Y | 2019-04-05
32866-1 | Wave 1 |  | Underway | 2019-08-28 | 2019-05-03 | Terry K | N | Y | 2019-04-26
7000037-132 | Wave 1 |  | ID'd Not Started | 2019-05-01 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
7000037-173 | Wave 1 |  | ID'd Not Started | 2019-05-01 | 2019-04-19 | Jennifer C | N | Y | 2019-04-12
1806M72G01 | Wave 2 |  | ID'd Not Started | 2019-11-01 | 2019-06-14 | Agatha B. | N | Y | 2019-06-07
1806M72G02 | Wave 2 |  | ID'd Not Started | 2019-11-01 | 2019-06-14 | Agatha B. | N | Y | 2019-06-07
2-310-046-09 | Wave 2 |  | ID'd Not Started | 2019-12-01 | 2019-05-24 | Ken H. | N | Y | 2019-05-17
4222115-1001 | Wave 1 |  |  |  | 2019-06-14 | John K | N | Y | 2019-06-07
65053853-1002 | Wave 1 |  |  |  | 2019-06-14 | John K | N | Y | 2019-06-07